## Sheet1
days | date | predected remining story points | actual remining story points
1 |  | 16 | 16
2 | 1399-04-12 | 13 | 13
3 | 1399-04-13 | 10 | 9
4 | 1399-04-14 | 6 | 7
5 | 1399-04-15 | 3 | 6
6 | 1399-04-16 | 3 | 4
7 |  | 0 | 0
| task to do | story points | assign to
| Design reminding Cards Shape | 3 | Amir Hossein - Mohammad
| Implementing Reminding Cards layout | 1 | Amir Hossein - Mohammad
| Write query of inserting reminder | 3 | Amir Hossein - Mohammad
| Write query of retrieving reminder | 3 | Amir Hossein - Mohammad
| Merging reminder layout with main page layout | 1 | Amir Hossein - Mohammad
| Merging reminders code with main page codes | 1 | Amir Hossein - Mohammad
| connect class elements to its appropriate layout element | 2 | Amir Hossein - Mohammad
| Test functionality | 1 | Amir Hossein - Mohammad
| Fixing bugs | 1 | Amir Hossein - Mohammad